## Sheet1
Time Trial Risk Assessment | V2
Notes | This Risk Assesssment is specific to an event involving only clubs on the reach.
It assumes that each club is operating within its own Covid risk assessment
It assumes that each club has made its members aware of the event
The severity of Covid19 obviously varies; 3 has been used as a compromise
Hazard | Consequence | Probability | Severity | Risk level pre-control | Mitigation | Responsible | Risk level post control
Large numbers of people in boathouse
In boathouse, getting boats out | being in fected with Covid19 through proximity in partially enclosed space | 2 | 3 | low | use masks when in boathouse for any reason, try and let others get their boat out first | members | low
On site, between boathouses, queuing to embark | being in fected with Covid19 through proximity outdoors | 1 | 3 | moderate | use masks, keep distancing | members | low
On site, between boathouses, cleaning boats between divisions | being in fected with Covid19 through proximity outdoors | 1 | 3 | low | use masks, keep distancing | members | low
Using indoor toilets | being in fected with Covid19 through proximity in partially enclosed space, and infection risk through touching surfaces | 3 | 3 | moderate | need a door monitor, three toilets so 3 people allowed in, need sanitiser etc | members and clubs
Difficulty in social distancing for volunteers@
in marshalling boats | being in fected with Covid19 through proximity outdoors | 2 | 3 | low | MIN to try to get single household crew and keep same crew for both divs. Avon County RIB is big enough for 2m social distancing | clubs | low
in safety boats when rescuing | being in fected with Covid19 through proximity outdoors, exacerbated by need to hold rescued person | 3 | 3 | moderate | do your best but risk of staying in cold water higher than risk of Covid, provide blanket and mask for casualty | members and safety boat crews | low
during race timing | being in fected with Covid19 through proximity outdoors | 1 | 3 | low | keep the spotter and watch timer 2m apart if poss | timers | low
helping on raft | being in fected with Covid19 through proximity outdoors, exacerbated by being close to rowers launching | 3 | 3 | moderate | raft helpers will only be provided if entry numbers dicate. Helpers to try not to lean over the rowers, masks for raft helpers | raft helpers | low
equipment handover | being in fected with Covid19 through proximity outdoors and touching surfaces | 3 | 3 | moderate | keep the same timers for both divisions, clean watches etc before and after | timers | low
River hazards ( always present but more important when racing )
paddle boarders going slowly and/or on the wrong side | collision, main risk to paddleboarder - damage or collision | 2 | 2 | low | keep a good look out, first aiders at Avon County and Minerva if needed | crews | low
sinking rafts | being in fected with Covid19 through proximity outdoors, through use of limited space on rafts | 2 | 3 | low | hoping to re float rafts before the race | Avon County | low
trees sticking into river, on Minerva side at 1250 and 250, on Avon side at 1000 and 1250 | collision damage to boat or rower | 3 | 2 | Low | keep a good look out, first aiders at Avon County and Minerva if needed | crews | low